## 09-23-2014
Serial	Tasks	Description	Resource	Comments	Status	Completion date
1	Report Maximisation	There should be 4 mini portlets. If user clicks on maxmize link of mini portlet then application should display corressponding maximize portlet. And there should be back link.	Rajesh
2	Incase of idle, show application login page	Suppose a user is idle for sometime and if user presses log out link then WebSphere Login page is coming instead of DST Potal login page.	Arathy
3	No links with Other application	Lotus connection login and DST Portal login issues. Login to one systems logs out the other	Arathy
4	Renaming the url to a meaningful name	.Instead of the current URL, think about a good name .... xxxx.in.dst.ibm.com xxxx = dial in case of DIAL	Paresh	Need to check with Dial team how they have done it. We may install IHS in development server.
5	Having meaningful content in home page	Home page should have meaningful content and eye catching.	Vijay/Rajesh
6	Comparing with PH ticketing report	Clean-up the ticketing report so that it looks readable and more meaningful to anyone looking at it (e.g current one is like a big inventory). May be we should take a look at the report PH Team is preparing and try to mimic the same screen experience	Kalai
7	Fixing Ticketing report defect	DST Portal application should always display calender and chart. Fix the defects in local first and then move to Development Server.	Shilpa and Kalai
8	Integrate Idash in DSTPortal application	We have some reports in Idash. Bring idash reports inside DSTPortal. IDASH application should internally take dstportal login/password and so it shouldn't ask userid/password. There should be SSO configuration between DSTPortal and IDASH. Currently same SSO configuration (between DSTPortal and Cognos) works well.	Shilpa	Previously worked

## 09-08-2014
Serial	Tasks	Resource	Comments	Status	Completion date
0	Deploying dstportal project in local and understanding the code.	Paresh,Arathy, Shilpa, Kalai	pre condition before starting task	Done	09/04/14
0.1	Explaing current code to team.	Rajesh	pre condition before starting task	Done	09/04/14
1	Removing DSTPortal word and add "My Portal" text at top of Login page.	Rajesh			09/10/14
2	Remove left navigation and move links at top of home page	Rajesh/Krishna	Low priority
3	Removing picture , requriment conent and adding welcome message in home page.	Rajesh			09/10/14
4	Setting up 4 portlets in single page.	Krishna			09/10/14
5	prepare mini portlet of inprogress ticketing report (first top 5 countries) which will be used when 4 portlets are displayed sametime.	Shilpa	Size 200 * 200. we can change it		09/09/14
6	prepare maximum portlet of inprogress ticketing report(All countries) which will be used when maximum button pressed for this portlet.	Shilpa			09/09/14
7	prepare mini portlet of on-hold ticketing report (first top 5 countries)which will be used when 4 portlets are displayed sametime.	kalai	Size 200 * 200. we can change it		09/09/14
8	prepare maximum portlet of on-hold ticketing report(All countries) which will be used when maximum button pressed for this portlet.	Kalai			09/09/14
9	prepare mini portlet of inprogress more than 30 ticketing report(first top 5 countries) which will be used when 4 portlets are displayed sametime.	Arati	Size 200 * 200. we can change it		09/09/14
10	prepare maximum portlet of inprogress more than 30 ticketing report(All countries) which will be used when maximum button pressed for this portlet.	Arati			09/09/14
11	prepare mini portlet of combined ticketing report(first top 5 countries) which will be used when 4 portlets are displayed sametime.	Shilpa	restapi not ready, need to check with Ajay
12	prepare maximum portlet of combined ticketing report (all countries)which will be used when maximum button pressed for this portlet.	Shilpa	restapi not ready, need to check with Ajay
13	cognos portlet alignment issue.	Paresh	Need to work with Syed/Bhavya		09/11/14
14	The legends to be in plain English . e.g. don't use underscore	Kalai	done but need to apply for restapi reports
15	Integrating different parts	Rajesh	depends on other portlets		09/11/14
16	Mock screen need to be developed. This would be reviewed with users to avoid unnecessary UI changes after going live.	Vijay/Krishna		Inprogress
17	Suppose a user is idle for sometime and if user presses log out link then WebSphere Login page is coming instead of DST Potal login page.	Krishna
18	Lotus connection login and DST Portal login issues. Login to one systems logs out the other.	Krishna
19	Need to resolve alignment issues of all reports.	Krishna
20	Comparing Philipines Ticketing reports with current one and fix it.	Kalai
21	Instead of the current URL, think about a good name .... xxxx.in.dst.ibm.com xxxx = dial in case of DIAL.	Vijay/Rajesh	Low priority. Need to install IHS at server